## Instructions
Asset Management Plan
Instruction to Agencies
Culture Agencies are to complete an Asset Management Plan for submission as part of their Business Plans. The attached template is to be used to facilitate the fulfillment of this requirement. The purpose of the Asset Management Plan is to report on ongoing capital projects and identify repair and rehabilitation initiatives to be undertaken over the planning horizon. Completing an Asset Management Plan presents agencies with an opportunity to inform the ministry of the progress of ongoing projects and to demonstrate the planning and undertaking of repair and rehabilitation projects both inside and outside of the scope of those approved by the ministry. It is expected that the projects described in this plan will align with asset renewal priorities identified in the Ministry's Asset Management Information System (AMIS), and will be consistent with the other components of the agency's Business Plan.

## Asset Management Plan
AGENCY NAME: |  | Ontario Library Service - North
FISCAL YEAR: |  | 2019-20
ASSET MANAGEMENT PLAN
Please refer to instructions to agencies on Tab #1
No. | Project Name | Project Description | New Project? Y/N | Total Cost $ | Capital funding provided by self-generated or operating funds $ | Partner (Private Sector) or Foundation funding $ | Expected contribution by MTCS $ | Expected contribution by other government partner $ | 2017-18 Actual Cost $ | 2018-19 Cost $ | 2019-20 Cost $ | 2020-21 Cost $ | Project Cost to be Expensed or Amortized? | Expected Start Date | Expected End Date | Project Rationale
01 | Insert Project Name | High-level description of project underway or planned. |  | Cost to complete entire project over planning horizon, as applicable. | Capital funds internally budgeted by agency. | Private sector or agency foundation funding contribution. | MTCS contribution requested or received. | Funding contribution anticipated from federal or municipal government. | Reporting on cost of prior fiscal- year's completed/ongoing projects. | Total cost of current fiscal year's ongoing projects. | Total Cost of future fiscal year's planned projects. | Total Cost of future fiscal year's planned projects. | Is or will the cost of the project be amortized or expensed? | When is the project expected to begin? | When is the entire project expected to be completed? | Please describe the significance of this project, including the following elements: a) alignment with asset renewal priorities identified in the Ministry's Asset Management Information System (AMIS); b) alignment with other components of the Business Plan (e.g. mandate, strategic directions); c) economic/financial impact (i.e. estimates of jobs created and revenue generated/savings achieved); and d) impact of (and contingency plan for) project delays.
1 | painting porch floor | sealing and painting concrete floor | Y | 1490 | 0 | 0 | 2103 | 0 | 1490 | 0 | 0 | 0 | expensed | 2017-06-01 | 2017-08-01 | C3020 floor finishes beyond useful life
2 | New computers for lab | upgrade eqmt used in testing, training | Y | 33000 | 0 | 0 | 33000 | 0 | 32340 | 0 | 0 | 0 | amortized | 2017-12-01 | 2018-02-01 | to upgrade eqmt used in testing and training
3 | table | large work table for skills advisors | Y | 1500 | 0 | 0 | 1500 | 0 | 1040 | 0 | 0 | 0 | amortized | 2017-12-01 | 2017-12-01 | to provide a better work space for large projects
4 | fire alarm system | replace detectors, alarm system | Y | 46064 | 0 | 0 | 46064 | 0 | 0 | 46064 | 0 | 0 | amortized | 2018-10-01 | 2019-03-01 | D5037 in AMIS, scheduled for replacement
5 | asphalt shingling over annex | replace shingles over porch roof | Y | 3246 | 0 | 0 | 3246 | 0 | 0 | 0 | 3246 | 0 | amortized | 2019-09-01 | 2019-09-01 | B30 Roofing beyond useful life
6 | ceiling finishes | ACT system renewal | y | 20250 | 0 | 0 | 20250 | 0 | 0 | 0 | 0 | 20250 | amortized | 2020-10-01 | 2020-11-01 | C3030 ceiling finishes Type C proactive replacement
7 | HVAC system | air ductwork distribution renewal | y | 74112 | 0 | 0 | 74112 | 0 | 0 | 0 | 0 | 74112 | amortized | 2020-11-01 | 2020-11-01 | D3040 distribution systems Type C proactive replacement
8 | exhaust system renewal | washroom fan replacement | y | 3269 | 0 | 0 | 3269 | 0 | 0 | 0 | 0 | 3269 | amortized | 2020-11-01 | 2020-11-01 | D3040 distribution systems Type C proactive replacement
9 | exterior lighting renewal | replace exterior lights | y | 1624 | 0 | 0 | 1624 | 0 | 0 | 0 | 0 | 1624 | amortized | 2020-10-01 | 2020-11-01 | D5022 Lighting Eqmt Type C proactive replacement
10 | renew lighting fixtures | renew fixtures in halls, stairwells, rooms | y | 8550 | 0 | 0 | 8550 | 0 | 0 | 0 | 0 | 8550 | amortized | 2020-12-01 | 2021-01-01 | D5022 Lighting Eqmt Type C proactive replacement
11 | plastic grate system | renew plastic grates | y | 14429 | 0 | 0 | 14429 | 0 | 0 | 0 | 0 | 14429 | amortized | 2021-01-01 | 2021-02-01 | C3030 ceiling finishes Type C proactive replacement
12 | renew roof membrane | renew single-ply roof membrane | y | 28333 | 0 | 0 | 28333 | 0 | 0 | 0 | 0 | 28333 | amortized | 2020-10-01 | 2020-11-01 | B30 Roofing Type C proactive replacement
13 | renew fencing | renew chain-link fencing | y | 30529 | 0 | 0 | 30529 | 0 | 0 | 0 | 0 | 30529 | amortized | 2020-09-01 | 2020-09-01 | G2041 Fences Type C proactive replacement