## Risks
Risk Worksheet | Agency Name ONTARIO LIBRARY SERVICE - NORTH Q2-November 2018
Risk | Related Strategic Priority | Impact & Scope Description (Consequences) | Likelihood and Impact | Mitigation Strategies (Action Plans) | Overall Risk Assessment | Risk/Mitigation Funded? | Risk Owner | Target Dates for Mitigation Strategies
Enter brief description of risk. | What strategic priority would risk affect? (If any, enter related objectives, goal or targets, etc) | Identify impact if risk occurs; both financial and non-financial (operational, reputation, etc). Review data, statistics or historical information where possible. Quantify consequences in relation to cost, quality, time (include exact figures and dates). | Likelihood: Low, Medium, or High Impact: Low, Medium or High | Mitigation strategies should not include 'asks' for increased provincial funding or resources. Please describe agency strategies to manage risk. Identify whether this strategy is already in place or when it will be implemented (with exact dates). Identify the expected residual risk remaining after strategy has been implemented. State current status of mitigation strategy. | Low, Medium, High | Has the cost of risk mitigation or entire risk been included in budget allocations? | Position responsible for mitigation strategy and ensuring issue or risk is managed.
Risk Category: | Strategic/Policy/Performance - risk that strategies and policies fail to achieve required/targeted results and do not properly support business needs; include stakeholder and public perception/reputation risks; potential underachievement of performance targets; and program objectives whose achievement is highly dependent on other initiatives.
That we have insufficient resources to complete goals of the strategic plan | Would impact ability to meet all strategic priorities | Would lose the ability to keep services relevant; lose faith of clients; and clients would experience loss of momentum in their growth | Likelihood: Medium Impact: High | Prioritize strategies which are achievable | Medium-Although it is very likely that financial resources may not allow for completion of all initiatives , it is less likely that the entire strategic plan would be jeopardized. | No | Board | Ongoing business planning and fiscal monitoring. Strategic Plan is based on current resources.
That one or more partners do not meet obligations of strategic initiatives as part of the provincial investments | Goal 3: To provide training that addresses the skills requirements of client libraries, delivered by the most effective means. | Initiatives would need to be picked up by other library partners. The impact on finance would be variable depending on the initiative | Likelihood: High Impact: Low | Continue to hold networking meetings with partners and to monitor progress of initiatives. Build awareness of capabilities of other partners should an initiative be in jeopardy. Monitor the future of organizations in question and minimize exposure | Low- It is likely that other organizations will work together to fill in the gap, due to level of agreement on initiatives | No | CEO | Ongoing business planning Collaboration has grown to include other library organizations
That we have insufficient resources to sustain current level of service. | Would impact ability to meet all strategic priorities | Loss of service; loss of faith of clients; loss of momentum in Northern Library development | Likelihood: High Impact: Medium | Prioritize strategies which are achievable | Medium-Elimination of staff position last year will affect service levels to some degree | No | Board | Ongoing business planning and setting of service priorities
Risk Category: | Governance/Organizational - include risks related to the organizations structure, accountabilities, or responsibilities; risks that culture and management commitment do not support formal structures, include controllership/accounting risks; and issues raised by staff, partners, stakeholders.
That the NOLS Board is unable to agree on particular strategies to move the organization forward. | Would impact ability to meet all strategic priorities | Interruption to service; loss of faith of clients | Likelihood: Low Impact: Medium | Provide extensive information to the Board on environment and potential strategies. Adhere to strategic planning process | Low- It is likely that other organizations will work together to fill in the gap, due to level of agreement on initiatives | Yes | Board | Strategic Plan in place
That the NOLS Board and management disagree on proposed strategies | Would impact ability to meet all strategic priorities | Interruption to service; loss of faith of clients | Likelihood: Low Impact: Low | Provide extensive information to the Board on environment and potential strategies. Adhere to strategic planning process | Low- It is likely that other organizations will work together to fill in the gap, due to level of agreement on initiatives | Yes | Board | Strategic Plan in place
That the Board be unable to meet the costs of the non recorded liability on employee future benefits. The cost of providing an annual valuation on this expense exceeds the yearly expense itself. | Would impact ability to meet all strategic priorities | As collective bargaining matter would be subject to arbitration. Would have financial impact on organization, and would erode services in all areas of our strategic plan | Likelihood: Low Impact: Low | Liability is managed as part of financial planning and budgeting | Low- annual cost of these benefits approx. $10,000; average staff age had decreased in past 10 years substantially | Yes | Board | Part of annual budget process and reviewing options for minimizing liabilities currently
Risk Category: | Legal/Compliance - include risk of litigation, risks from non-compliance to applicable laws, acts, and policies, and risks related to contract management
That we are unable to meet the requirements of the AODA | Would impact ability to meet all service priorities | Client complaints would lead to legal repercussions. Failure to model for library clients may lead to less compliance on part of libraries | Likelihood: Low Impact: Low | Consultant developed plan and gap analysis. | Low-Process underway to resolve | Yes | CEO | Ongoing implementation of plan continues
Risk Category: | Operational/Service Delivery - include risks that products or services will not be completed or delivered as expected; capital or other project delays; level of program efficiency, effectiveness, customer.
That we are unable to meet rising costs within our operational budget, requiring service cuts to our finance and administration areas | Would impact ability to meet all service priorities | Our finance and administration team provide service support in the areas of pools, revenue development and consortial purchasing. It is likely that these services could no longer be provided at the same level without this support. | Likelihood: High Impact: High | Continue to review alternative sources of revenue when opportunities arrive and plan for transitional costs | High | Yes | Board and CEO | Position eliminated in 2016 to meet 2017-2018 and 2018-2019 budget targets
That we are unable to encourage library collaboration in sharing resources | Failure to meet part of mandate or Goal 1: To encourage library collaboration to build library capacity. | In this time of constant changes in technology and economic restraint at all levels of government it is crucial for libraries to collaborate at all levels. If libraries fail to collaborate, in areas like JASI, interlibrary loan etc, services will not be affordable for all and certain services would be unsustainable | Likelihood: Low Impact: Medium | Continue to train advisors to promote collaboration | Low-Libraries high motivation to move forward | No | CEO | Ongoing Service Planning
That our services become irrelevant to our clients | Would impact ability to meet all strategic priorities - should we become irrelevant - none of our service goals would be of value to clients | Stalling of library development in Northern Ontario; usage declines | Likelihood: Low Impact: High | Continue to conduct user surveys; work with advisory groups and do strategic planning | Low- Mitigation strategies embedded in operations | Yes | CEO | User Survey completed every 3 years (April 2017); ongoing service planning
That we do not properly address our clients' needs | Would impact ability to meet all strategic priorities - should we become irrelevant - none of our service goals would be of value to clients. This will become more likely with loss of position in finance and administration | Stalling of library development in Northern Ontario; usage declines; agency unable to sustain itself | Likelihood: Low Impact: High | Continue to conduct user surveys; work with advisory groups and do strategic planning | Low- Mitigation strategies embedded in operations | Yes | CEO | User Survey completed every 3 years (April 2017); ongoing service planning
That clients are not aware of the services we provide | Would impact all goals but especially Goal 4: To engage CEOs, Staff, Boards in the identification and evaluation of their skill sets, roles and responsibilities. | Stalling of library development in Northern Ontario; lower usage of vital services | Likelihood: Low Impact: Medium | Develop and implement marketing plan and maximize the use of library visits and social media | Low- Mitigation strategies imbedded in strategic plan | Yes | CEO | Marketing plan in place
That clients are dissatisfied with the decision to eliminate services in order to balance the budget | Would impact ability to meet all strategic priorities | Could create negative feedback and communications which reflect negatively on the organization | Likelihood: Medium Impact: Medium | Communicate clearly with clients regarding the reasons for the decisions and target services which are less connected to core business. | Medium | Yes | CEO | Ongoing as decisions are made and implemented
That we are unable to meet the demand of libraries for JASI due to insufficient resources | Goal #4: Encourage libraries to be leaders in adopting creative and innovative approaches to service delivery | JASI is one of the platforms used for client collaboration. Libraries will need to take on more or all costs to continue service as time proceeds unless other sources of revenue are found. | Likelihood: Medium Impact: high | Communication Plan for Service | Medium | Yes | CEO | Moved to cost recovery model in 2015. OLS staff time not included in calcuation of cost
Risk Category: | Workforce - include workforce compensation, labour relations and human resources risks; workforce data showing thigh turnover, imminent retirement, high illness rates, staff complaints
That we are unable to reach a resolution to a grievance initiated by the union | Would impact ability to meet all strategic priorities | Cost of enforced resolution leads to cuts to other services | Likelihood: Low Impact: Low to Medium | Continue to have active Labour - Management committee to resolve issues | Low | Yes | CEO | Ongoing
That we are unable to attract skilled staff to positions in Northern Ontario | Would impact ability to meet all strategic priorities | Insufficient resources to meet the needs of clients; additional costs to contract services | Likelihood: Medium Impact: Medium | Continue to use recruitment resources to find suitable candidates | Medium | Yes | CEO | Ongoing
That we are unable to agree on the terms of a new collective bargaining agreement with the union | Would impact ability to meet all strategic priorities | Work stoppage could halt many services | Likelihood: Medium Impact: High | Continue to negotiate with the parties to reach a satisfactory agreement; Review work stoppage protocals and prepare to implement if necessary | Medium |  | Board | CBA in place
Staff Injury especially while travelling | Would impact ability to meet strategies which involve the staff member; and all other priorities should it have a financial impact | Costs of transporting staff member home; loss of productivity; increase in insurance premiums; possible law suits | Likelihood: Low Impact: Low | Staff Emergency kits and cell phones available; health and safety committee in place | Low | Yes | CEO | Ongoing
Risk Category: | Information Technology & Infrastructure - include capital project delays, risks related to organizational assets, physical safety and security risks
That electronic records are lost due to technical failure | Would impact ability to meet all strategic priorities- as parts of history and contact information could be lost | Costs of repair; use of staffing resources to rebuild lost documentation | Likelihood: Low Impact: Low to Medium | Proper back up procedures in place | Low | Yes | CEO | Complete
Risk Category: | All other Risks - Risks that do not fit in any of the above categories. Corporate Social Responsibility concerns - Environment, Climate Change, Energy Management , Health Promotion, Waste Reduction. Include risks relating to third parties such as service or goods providers.
Facility Crisis | Would impact ability to meet all strategic priorities- as could have a large impact on finances and productivity | Costs of repair or relocation; loss of productivity | Likelihood: Low Impact: Medium to High depending on the nature of the crisis | General upkeep of facility; insurance in place, regular inspections of heating systems, roof and alarms | Low | Yes | Board | Ongoing
Note: | The Ontario Public Sector corporate risk categories do not include a separate 'Financial Risk' category. Every risk can have financial and or non-financial impact, as such, the financial impact should be assessed for every risk. If meeting financial budgets/commitments is of concern, risks causing these shortfalls should be identified.